## Example 1
Project Charter
Immigraniada
Problem Statement |  | Business Case & Benefits
Immigration procedures are complicated for everyone, even for people that have a background on how to deal with laws and regulations. As of now, Immigration Canada is behind on more than 60% of the processes that are currently awaiting analysis. The backlog is immense, and more people become apt to or have to request a status extension. One of the main issues is that if you get it rejected for not knowing the proper procedure, you may lose your status or have some parts of it (the ability to work for a student, for example) jeopardized. Thinking of that we wanted to give students and workers applying for their permits in Canada the opportunity to understand what they need in a simple, quick and easy way. |  | Canada receives more than 200.000 immigrants every year, coming on study and work permits, alone or with their families. There aren't a lot of companies that offer a simplified way of checking your documents when filing the application by yourself, and the ones that do are really expensive, with prices starting from CAD $120-150. The opportunity is evident.
Goal Statement |  | Timeline
Provide a tool that's easy and intuitive that outputs the immigration forms to the user with the user's own information, in a way that all he has to do is copy it into the actual form. User should be able to do the entire process in less than 60 minutes. |  | Phase | Planned Completion Date |  | Actual
|  | Define: | Nov 17th |  | Done
|  | Develop: | Dec 07th |  | Dec 07th
|  | Analyze: | Dec 15th |  | Pending
|  | Improve: | Dec 15th |  | Pending
|  | Control: | To be defined |  | Pending
Scope In/Out |  | Team Members
1st Process Step | Applicant accesses the landing page for the application | Position | Person | Title | % of Time
Last Process Step | Form (or forms) are returned as a view to the applicant(s) with his/her/their own information filed, to serve as reference | Team Member | Henrique | Developer | 50%
|  | Team Member | Iana | Developer | 50%
In Scope: | Study Permit request and extension, Work permit request and extension, family information, follow IRCC updates and changes on the forms and/or procedures
Out of Scope: | Actual application, immigration advising, visitor visa (to be implemented soon)